## Slide 1
CS 498
  Virtual Reality
  Production & Design Processes
    (For internal use only)

## Slide 2
Project Schedule Update
Pre-Production Deadline: October 25, 2019 23:59pm
Deliverables:
  Updated Canvas, game loop and World/Environment docs
    Should incorporate any feedback from Discovery
  Feature List: Created from the Canvas Core Pillars and Core Systems
  TDD: Created from the Feature list
    A more detailed breakdown of the programmatic elements and assets needed
  Milestone Schedule: 1st pass at what will be done when and by who
  QA Test Plan:
    Each element of the TDD should be broken down into testable elements.

## Slide 3
Why do project management (production in video games)?
Project success = completing planned deliverables, within budget and on time (including approved changes))
If you define success as listed above, most companies have a success rate of?
  30% (In a study of 10,640 projects from 200 companies in 30 countries and across various industries, it was found that only 2.5% of the companies successfully completed 100% of their projects.)
Reasons for failure
  Lack of confidence in project success: 75% of respondents admit that their projects are either always or usually “doomed right from the start.”
  Rework wariness: 80% admit they spend at least half their time on rework.
  Project out of sync: 78% feel the business is usually or always out of sync with project requirements
  Fuzzy objectives: Only 55% feel that the business objectives of their projects are clear to them.
Notes: First time Project Development without project management is like being blindfolded and being led into a big room for the first time. You stumble around tripping over things and slowly a picture of the room will develop in your head but you are never quite sure where you are going. Sequels are when you take the blindfold off and scan the room for a long time, put it back on and then someone comes into the room and adds furniture. Project Management is basically someone describing the room to you while looking at an accurate but blurry picture of the room. It’s a tool that helps you understand the space you are in.

## Slide 4
What is Production and why does it matter?
Production drives:
The creation of an atmosphere to support Productivity
Planning (staffing)
Budgeting
Team Communication
  Provides the eyes and ears for studio leadership into the team progress and overall mental state
Risk management
Decisions around scope and feature development
Copyright Gamasutra: Cognitive Flow: The Psychology of Great Game Design

## Slide 5
Old School production processes
The infamous Task List
Loved by many a programmer
Often driven by preference
  Doesn’t consider dependencies
The Hive mind
Used by small teams usually working in one room
  Everyone knows what everyone is doing so planning isn’t as necessary
Doesn’t pass “the bus test”
Doesn’t deal with scope or “creative direction” and can be an issue with dependencies

## Slide 6
A Simple Project Plan
Contains:
High and mid-level Design Elements
  Vision Canvas
  Feature List (notice the reference numbers, they are important)
  Action Loops
Simple Technical Design Doc
Simple Milestone doc (instead of a true schedule)
QA test plan

## Slide 7: Simple Feature List
Number | Feature | Top Level Description | Priority | Difficulty | Time To Implement | Risk/Considerations | Comments
F001 | Melee Combat | Primary combat system | High | High | High | Animations may require modifications to the animation system | 
 |  |  |  |  |  | Camera system needs to pan relative to the attack type | 
 |  |  |  |  |  | VFX needs to differ for each weapon (may impact schedule) | 
F002 | Quadripeds | We want to support enemies with 4 legs | High | High | High | The volume of animations | We may be able to use the regular system and fake it
F003 | Clouds | Add moving clouds to the sky dome | Low | Moderate | High | New system | Nice to have if possible
 |  |  |  |  |  | Players may expect weather | 
F004 | Cover | Ability to hide behind objects | Med | Med | Med | Objects need to be of certain heights, specs need to be created | Would make the combat system more interesting
 |  |  |  |  |  | May add complexity to the combat swings | 

## Slide 8
Technical Design Document: Built from the Feature List
Breaks down the Feature List into technical appropriate segments
Specifics will be programming elements
Systems (combinations of related tasks/features)
One-off features
Clarifies the priorities, risks and dependencies

## Slide 9
Ver 1.1 | Modified 9/11/2018 |  |  |  |  |  |  | 
Ref # | System Name | Feature Supported | Feature Specifics | Priority | Difficulty | Risk | Time Estimation | Comments
F001 | Traversal |  |  |  |  |  |  | 
F001a |  | Camera |  | High | Med | Low |  | 
 |  |  | View Frustum |  |  |  |  | To Be determined
 |  |  | Viewing Distance (Scale) |  |  |  |  | Based on Frustum
F001b |  | Controls |  | Med | Low | Low |  | Timing based on Environmental layout
 |  |  | Walk |  |  |  |  | 
 |  |  | Run |  |  |  |  | 
 |  |  | Jump |  |  |  |  | 
 |  |  | Crouch |  |  |  |  | 
F001c |  | Determine Player Location |  | Low | Low | Low |  | 
F002 | Melee Combat |  |  |  |  |  |  | 
F002a |  | Camera |  | High | Med | Med |  | 
 |  |  | Over the Shoulder |  |  |  |  | 
F002b |  | Controls |  | High | Med | Low |  | 
 |  |  | Thrust |  |  |  |  | 
 |  |  | Swing |  |  |  |  | 
 |  |  | Counter |  |  |  |  | 
 |  |  | Block |  |  |  |  | 

## Slide 10
Milestone Plan
Weekly or Bi-weekly set of tasks to be done by the team
Tracked to:
  Show progress
  Expose scope issues
    You need to consider assets as well as systems/routines
  Determine risks
  Ensure that the correct dependencies are being considered
DEPENDENCIES
  Can be a huge time waster, work waits while a dependency is completed

## Slide 11
Simplified Project Plan
Project: | Your Project name goes here |  |  |  | 
Date | Milestone | Task | Assets Needed | % Complete | Comments
1/30/19 | Design |  |  |  | 
 |  | Create Vision Canvas | None |  | 
 |  | Create Tone Target | None |  | 
 |  | Create Art Spectrum | None |  | 
2/15/19 | Design II |  |  |  | 
 |  | Create Tech Design Doc | None |  | 
 |  | Create Feature List | None |  | 
 | Feature I |  |  |  | 
 |  | Ex: Inital Play Area layout | Example: Initial UI elements |  | 
 |  |  | Initial Contact Interface |  | 
 |  |  | Initial Movement System, etc |  | 
Insert New Dates | Insert new Milestones | Insert New Tasks | Insert New Asset Lists |  | Add new rows to include new milestones, add as many as you need

## Slide 12
Quality Assurance (QA) Test Plan
Details out the elements of each feature to ensure it is working properly
Once you reach Alpha the test plan becomes key to a successful User Experience
Have someone not on the team, run through the test plan
Remember to test integration, where system interact and work together
  Most often failures occur here

## Slide 13
QA Test Plan |  | Project:_____________________________ | 
Date | Build # | Tester Name | 
1/14/2019 |  |  | 
Test # | Unit/Feature | Item to be Tested | Success/Fail
1 | Main Screen |  | 
1a |  | Game Loads properly to Main Screen | 
1b |  | UI elements change focus correctly | 
1c |  | Choosing <Start Game> functions correctly by placing the player in the game at the beginning of the first element | 
1d |  | Choosing <Exit Game> functions correctly closing out the game cleanly and places the player back in the platform interface | 
1e |  | Choosing <Load Saved Game> functions correctly takes the player to the <Save/Load Game system | 
1f |  | Choosing <Settings> functions correctly by taking you to the Player Setting System | 
2 | Performance |  | 
2a |  | Game loading time is within spec (loads within XX seconds) | 
2b |  | General game play shows no hitching or graphic errors | 
3 | Save Game |  | 
3a |  | Game save time is within spec (saves within XX seconds) | 
3b |  | Saved Game can be reloaded immediately | 
3c |  | Saved Game Data is correct on reloading | 

## Slide 14: VR Design: Project Review and Critique
BeatDance: https://www.youtube.com/watch?time_continue=5&v=fKkAAEalfXA
Code 23: https://www.youtube.com/watch?time_continue=1&v=qekKBFw-1jA
Culture Heritage Site (Cahokia Mounds): https://www.youtube.com/watch?v=OXXnKjPWmvo
Death Mine: https://www.youtube.com/watch?v=EJR-f2GgGSY
Doctor Dodge: https://www.youtube.com/watch?v=FdJu5SsqOOI
Dungeon Crawler: https://www.youtube.com/watch?time_continue=6&v=AzK8fJNOqcs
ECE 329: https://www.youtube.com/watch?time_continue=7&v=Y7-QghC1wgk
Elemental Experience: https://www.youtube.com/watch?v=xnmZ9F3VdKM
Event Horizon: https://www.youtube.com/watch?v=8dithIiWFaw